## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | User Authentication | Authentication | As a user, I want to securely access the app so that my personal information and data remain protected | Must | In Progress | 1. The user can register with a valid email and password. 2. User receives a confirmation email for account activation. 3. User can log in with registered credentials. 4. Password reset functionality is secure and straightforward. | Secure password hashing and storage.- Account lockout after multiple failed login attempts. | Response time for authentication actions should be less than 2 seconds. Password reset emails should be delivered within 5 minutes. | 5 days | 4 days
2 | Mobile Optimization | Optimization | As a mobile user, I want a seamless experience so that I can navigate and use the app efficiently without any interruptions or difficulties | Should | Pending | 1. UI/UX is responsive on various screen sizes. 2. All features are accessible and functional on mobile devices. 3. Testing on multiple devices validates responsiveness. | Implement a mobile-friendly layout and navigation.- Ensure touch-friendly interactions. | Page load time on mobile devices should be less than 3 seconds.- App should support the latest versions of major mobile browsers. | 5 days | 5 Days
3 | Social Media Integration | Integration | As a user, I want to share app content on social media so that I can easily spread interesting or useful information with my friends, family, or followers | Could | Backlog | 1. User can share posts on linked social media accounts. 2. Shared posts display correctly on the respective social media platforms. 3. Social media API responses are handled gracefully. | Integrate with social media APIs (e.g., Facebook, Twitter).- Implement sharing options in the app's UI. | Response time for social media API calls should be less than 1 second.- Handle API rate limits and errors effectively. | 7 days
4 | Multi-language Support | Localization | As a global user, I want to use the app in my preferred language so that I can comfortably understand and interact with the content and features provided | Must | Ready for Dev | 1. User can select preferred language in settings. 2. All app content is displayed in the selected language 3. Translations are accurate and culturally sensitive. | Implement language selection in user settings.- Use localization for all UI text and content. | Translation process should be documented and repeatable.- Support at least 5 major languages. | 7 days
5 | Performance Enhancement | Performance | As a user, I want a fast and responsive app so that I can quickly accomplish my tasks without experiencing delays | Must | In Testing | 1. App loads within 3 seconds on average. 2. Smooth navigation between screens without delays. 3. Load testing confirms stability under peak usage. | Optimize database queries and indexing.- Implement caching for frequently accessed data. | Response time for critical user actions should be less than 2 seconds.- Monitor and optimize server resource usage.
6 | Offline Mode | Offline | As a user, I want to use the app without an internet connection so that I can access its features and information even when I am offline | Should | Backlog | 1. Users can access saved content without an internet connection. 2. Offline changes sync seamlessly when the device reconnects. 3. Conflict resolution is handled gracefully in case of sync issues. | Implement local storage for offline content.- Develop a syncing mechanism for offline changes. | The syncing process should be transparent to the user.- Offline mode should be functional for at least 80% of app features.
7 | Feedback Mechanism | Feedback | As a user, I want to provide feedback on the app so that the developers can improve the user experience and address any issues | Could | Backlog | 1. Users can submit feedback through the in-app form. 2. Feedback is recorded and visible to admin in the admin dashboard. 3. Feedback form includes necessary user information for follow-up. | Create a feedback form in the app. Implement a backend system to store and retrieve feedback. | Feedback should be stored securely and be accessible only to authorized personnel.- Admins should receive email notifications for new feedback submissions.
8 | Data Analytics Integration | Analytics | As a stakeholder, I want to gather insights from user data so that I can make informed decisions to enhance the app's features and overall performance | Could | Ready for Dev | 1. Integration with Google Analytics is successful. 2. Key user interactions and events are tracked. 3. Analytics dashboard provides actionable insights. | Implement Google Analytics SDK in the app.- Define custom events for important user actions. | Analytics data should be updated in near real-time.- Regularly review and analyze analytics data for decision-making.
9 | Bug Fixes | Bug Fixes | As a user, I want a bug-free experience so that I can use the app smoothly without encountering any issues or disruptions | Must | In Progress | 1. Resolved login error for users with special characters in passwords 2. Fixed image loading issue in the gallery. 3. Regression testing confirms bug resolution. | Identify and fix specific bugs reported by users and testing.- Implement automated tests to prevent regression. | Critical bugs should be resolved within 48 hours of discovery. Implement a bug-tracking system for efficient reporting and resolution.
10 | Enhanced Search Functionality | Search Enhancement | As a user, I want to find content easily so that I can quickly access the information I need without wasting time searching | Should | Backlog | 1. Search results are relevant and displayed in order of relevance. 2. Filters work correctly, refining search results. 3. User testing validates improved search experience. | Improve search algorithms for relevance.- Enhance filtering options based on user feedback. | Search queries should return results within 2 seconds.User satisfaction with search functionality should increase by 20% based on feedback.